## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Azure_Stack_Hub_Single_Scale_Unit_Deployment_ver_003 | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 0
1 | Yes | Auto Scheduled | PO issued by customer | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 1
2 | Yes | Manually Scheduled | Communincation Plan | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 1
3 | Yes | Manually Scheduled | Commuincations plan and Team members identified | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
4 | Yes | Manually Scheduled | Customer Cloud transformation executive sponsor | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
5 | Yes | Manually Scheduled | Customer deployment manager | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
6 | Yes | Manually Scheduled | Customer Operations Team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
7 | Yes | Manually Scheduled | Customer DevOps Team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
8 | Yes | Manually Scheduled | Customer Data Center Team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
9 | Yes | Manually Scheduled | Customer Migration Team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
10 | Yes | Manually Scheduled | Customer Cloud workload team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
11 | Yes | Manually Scheduled | Customer Networking Team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
12 | Yes | Manually Scheduled | Customer Security Team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
13 | Yes | Manually Scheduled | OEM Deployment team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
14 | Yes | Manually Scheduled | OEM Support point of contact (TAM or CSAM) | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
15 | Yes | Manually Scheduled | Microsoft Support CSAM [TAM] | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
16 | Yes | Manually Scheduled | Microsoft Cloud Solution Architect | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
17 | Yes | Manually Scheduled | Define communincation plan for deployment | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM | 4,5,6,7,8,9,10,11,12,13,14,15,16 | 3
18 | Yes | Manually Scheduled | Point of Contact for each stakeholder/team | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
19 | Yes | Manually Scheduled | Cadence and context of communincations | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
20 | Yes | Manually Scheduled | Escalation process for roadblocks | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
21 | Yes | Manually Scheduled | Send out initial communication | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM | 18,19,20 | 4
22 | Yes | Manually Scheduled | Pre-Deployment | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 1
23 | Yes | Manually Scheduled | Pre-deployment process started with OEM | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
24 | Yes | Manually Scheduled | Schedule initial deployment meetings with teams | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
25 | Yes | Manually Scheduled | Physical SU Placement identified | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
26 | Yes | Manually Scheduled | Power connections ready for SU placement | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
27 | Yes | Manually Scheduled | Network connections ready for SU placement | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
28 | Yes | Manually Scheduled | Identity | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
29 | Yes | Manually Scheduled | Connected or Disconencted deployment | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
30 | Yes | Manually Scheduled | AAD or ADFS | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
31 | Yes | Manually Scheduled | Networking | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
32 | Yes | Manually Scheduled | Timer server identified and configuration determined | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
33 | Yes | Manually Scheduled | DNS namespace format defined | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
34 | Yes | Manually Scheduled | Public IP Subnets defined | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
35 | Yes | Manually Scheduled | Firewall rules added to accomidate | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
36 | Yes | Manually Scheduled | Proxy type identified | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
37 | Yes | Manually Scheduled | NVA or VPN use for direct subnet access | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
38 | Yes | Manually Scheduled | Network routes identified | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
39 | Yes | Manually Scheduled | BGP or Static route to TOR | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
40 | Yes | Manually Scheduled | Load Balacing configuration defined | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
41 | Yes | Manually Scheduled | Security | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
42 | Yes | Manually Scheduled | Roles created for deployment | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
43 | Yes | Manually Scheduled | Roles created for operations | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
44 | Yes | Manually Scheduled | PKI | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
45 | Yes | Manually Scheduled | Certificates created | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
46 | Yes | Manually Scheduled | Pre-Deployment planning with Cloud Solution Architect | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
47 | Yes | Manually Scheduled | Training | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
48 | Yes | Manually Scheduled | Right sizing workloads | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
49 | Yes | Manually Scheduled | VM baselining | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
50 | Yes | Manually Scheduled | IO |  |  |  |  | 6
51 | Yes | Manually Scheduled | CPU |  |  |  |  | 6
52 | Yes | Manually Scheduled | RAM |  |  |  |  | 6
53 | Yes | Manually Scheduled | Containers | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
54 | Yes | Manually Scheduled | <New Task> | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
55 | Yes | Manually Scheduled | DevOps | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
56 | Yes | Manually Scheduled | API | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
57 | Yes | Manually Scheduled | PowerShell | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
58 | Yes | Manually Scheduled | Cloud Operations | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
59 | Yes | Manually Scheduled | OEM Process | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
60 | Yes | Manually Scheduled | Azure Process | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
61 | Yes | Manually Scheduled | Workload Plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
62 | Yes | Manually Scheduled | Redeploy Plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
63 | Yes | Manually Scheduled | Right size VM plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
64 | Yes | Manually Scheduled | Gather CPU requirements | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
65 | Yes | Manually Scheduled | Gather RAM Requirments | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
66 | Yes | Manually Scheduled | Gather Disk Requirements | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
67 | Yes | Manually Scheduled | Define VM Sizes based on requirments | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
68 | Yes | Manually Scheduled | VM Deployment | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
69 | Yes | Manually Scheduled | Migration tool identified | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
70 | Yes | Manually Scheduled | Schedule maintenace window | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
71 | Yes | Manually Scheduled | Netowork changes defined | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
72 | Yes | Manually Scheduled | Finalize migration plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
73 | Yes | Manually Scheduled | Refactor workload plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
74 | Yes | Manually Scheduled | VM to Containers | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
75 | Yes | Manually Scheduled | Database Services - Database migrations | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
76 | Yes | Manually Scheduled | App service | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
77 | Yes | Manually Scheduled | Serverless | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
78 | Yes | Manually Scheduled | Reimagine Workload Plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
79 | Yes | Manually Scheduled | Build out ARM scripts in Azure Global usign version profiles | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
80 | Yes | Manually Scheduled | Operations Plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
81 | Yes | Manually Scheduled | Backup / BCDR | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
82 | Yes | Manually Scheduled | Backup Plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
83 | Yes | Manually Scheduled | Cloud Infrastructure | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
84 | Yes | Manually Scheduled | SMB Share placement for Cloud infra | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 7
85 | Yes | Manually Scheduled | Sandbox ASDK for Infra backup testing identified | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 7
86 | Yes | Manually Scheduled | Tenant Workload backup plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
87 | Yes | Manually Scheduled | Non-Production Workloads | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 7
88 | Yes | Manually Scheduled | Production Workloads | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 7
89 | Yes | Manually Scheduled | DR plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
90 | Yes | Manually Scheduled | Local DR planning | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
91 | Yes | Manually Scheduled | Regional planning | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
92 | Yes | Manually Scheduled | Business Continuity | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
93 | Yes | Manually Scheduled | Patch and Update process defined | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
94 | Yes | Manually Scheduled | Billign and Charge back plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
95 | Yes | Manually Scheduled | Tagging | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
96 | Yes | Manually Scheduled | Resource Group | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
97 | Yes | Manually Scheduled | Quota/Subscription | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
98 | Yes | Manually Scheduled | 3rd party billing tool | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
99 | Yes | Manually Scheduled | API Integration Plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
100 | Yes | Manually Scheduled | Gap planning | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
101 | Yes | Manually Scheduled | Workload Gap | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
102 | Yes | Manually Scheduled | Operations Gap | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
103 | Yes | Manually Scheduled | Regulatory/Compliance Gap | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
104 | Yes | Manually Scheduled | Deployment | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 1
105 | Yes | Manually Scheduled | Cloud Region Deploymnet process | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
106 | Yes | Manually Scheduled | DC01 | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
107 | Yes | Manually Scheduled | SU1 | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
108 | Yes | Manually Scheduled | Physical Install | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
109 | Yes | Manually Scheduled | SU installed and secured | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
110 | Yes | Manually Scheduled | Power connected to PDU's | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
111 | Yes | Manually Scheduled | Network connections from TOR to Border established | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
112 | Yes | Manually Scheduled | OEM Integration script deployed | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
113 | Yes | Manually Scheduled | Network integration | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
114 | Yes | Manually Scheduled | Public IP Subnet tested against UAT created VM | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
115 | Yes | Manually Scheduled | MPLS/Express Routes Circuits updated to accomidate new route tables | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
116 | Yes | Manually Scheduled | NVA deployed (Sonicwall) | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
117 | Yes | Manually Scheduled | Test VPN conenctivity to SU1 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
118 | Yes | Manually Scheduled | Test Remote User connectivity into SU1 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
119 | Yes | Manually Scheduled | Test HLB (Sonicwall) | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
120 | Yes | Manually Scheduled | Identity System Integration | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
121 | Yes | Manually Scheduled | Create RBAC roles | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
122 | Yes | Manually Scheduled | Service Engineering Integration | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
123 | Yes | Manually Scheduled | Operations Monitoring Integration | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
124 | Yes | Manually Scheduled | Ticketing System | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
125 | Yes | Auto Scheduled | Logging System | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
126 | Yes | Manually Scheduled | Endpoint management | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
127 | Yes | Manually Scheduled | Run Azure Infra backup | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
128 | Yes | Manually Scheduled | Deploy Ops Console | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
129 | Yes | Manually Scheduled | Conenct Visual Studio Code to arm endpoint | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
130 | Yes | Manually Scheduled | Test API Intergration | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
131 | Yes | Manually Scheduled | Run UAT Script (Creates Offer and deploys test VM in HA config) | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
132 | Yes | Manually Scheduled | Migration tool selected | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
133 | Yes | Manually Scheduled | Backup tool integration | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
134 | Yes | Manually Scheduled | Monitoring System Integrations | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
135 | Yes | Manually Scheduled | Communincation plan | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
136 | Yes | Manually Scheduled | Right size VM's | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
137 | Yes | Manually Scheduled | Define VM sizes | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
138 | Yes | Manually Scheduled | Capacity Management | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 5
139 | Yes | Manually Scheduled | Assigned Subscriptions | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
140 | Yes | Manually Scheduled | Offers | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
141 | Yes | Manually Scheduled | Plans | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
142 | Yes | Manually Scheduled | Quotas | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 6
143 | Yes | Manually Scheduled | Adjust quotas for predinfed limits (may require support) | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 7
144 | Yes | Manually Scheduled | Tenant Workload Placement | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
145 | Yes | Manually Scheduled | VM Migration | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
146 | Yes | Manually Scheduled | Phase 1 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
147 | Yes | Manually Scheduled | Phase 2 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
148 | Yes | Manually Scheduled | Phase 3 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
149 | Yes | Manually Scheduled | Phase 4 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
150 | Yes | Manually Scheduled | Phase 5 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
151 | Yes | Manually Scheduled | Phase 6 | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
152 | Yes | Manually Scheduled | Run deployment scripts for new workloads | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
153 | Yes | Manually Scheduled | Refactor workloads | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
154 | Yes | Manually Scheduled | New deployment workloads | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
155 | Yes | Manually Scheduled | Billing | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
156 | Yes | Manually Scheduled | AHUB Script to be run | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
157 | Yes | Manually Scheduled | Operations Acceptance | 1 day? | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 1
158 | Yes | Manually Scheduled | Networking validation | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
159 | Yes | Manually Scheduled | Monitoring validation | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
160 | Yes | Manually Scheduled | Backup validation | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
161 | Yes | Manually Scheduled | BC/DR validation | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
162 | Yes | Manually Scheduled | Security validation | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
163 | Yes | Manually Scheduled | End point management validation | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
164 | Yes | Manually Scheduled | Service Engineering | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
165 | Yes | Manually Scheduled | MSFT Support Sev B ticket creation | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
166 | Yes | Manually Scheduled | Ensure SU subscription is included and or aligned with Support agreement | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
167 | Yes | Manually Scheduled | Create Sev B case to finalize deployment | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
168 | Yes | Manually Scheduled | Break glass - Adjust quotas | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
169 | Yes | Manually Scheduled | DevOps | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
170 | Yes | Manually Scheduled | API Connectivity verified with ARM | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
171 | Yes | Manually Scheduled | Patch and Update | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 3
172 | Yes | Manually Scheduled | OEM | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
173 | Yes | Manually Scheduled | Azure Hotfixes | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
174 | Yes | Manually Scheduled | Azure Full Updates | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 4
175 | Yes | Manually Scheduled | Deployment Post Mortem | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 1
176 | Yes | Manually Scheduled | Process changes needed | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
177 | Yes | Manually Scheduled | Lessons learned | 1 day | January 27, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units